## Sheet1
WORK BREAKDOWN SCHEDULE
WBS | Task | Owner | Start | End | Pred
Planning Phase
1.1 | Requirements Finalization | Jibran | 2026-01-22 | 2026-01-31
1.1.1 | Gather Stakeholder Requirements | Jibran | 2026-01-22 | 2026-01-26
1.1.2 | Document Requirements | Jibran | 2026-01-27 | 2026-01-30 | 1.1.1 Gather Stakeholder Requirements
1.1.3 | Sponsor Sign-Off | Jibran | 2026-01-31 | 2026-01-31 | 1.1.2 Document Requirements
1.2 | System Architecture Approval | Jibran | 2026-02-01 | 2026-02-10 | 1.1.3 Sponsor Sign-Off
1.2.1 | Design System Architecture | Jibran | 2026-02-01 | 2026-02-05
1.2.2 | Internal Architecture Review | Jibran | 2026-02-06 | 2026-02-08 | 1.2.1 Design System Architecture
1.2.3 | Architecture Approval | Jibran | 2026-02-09 | 2026-02-10 | 1.2.2 Internal Architecture Review
1.3 | Mid-Sprint Review | Kainat | 2026-02-18 | 2026-02-21 | 1.2.3 Architecture Approval
1.3.1 | Prepare Progress Report | Kainat | 2026-02-18 | 2026-02-19
1.3.2 | Conduct Review Meeting | Kainat | 2026-02-20 | 2026-02-21 | 1.3.1 Prepare Progress Report
Development Phase
2.1 | Booking Web App Development | Maaz | 2026-02-04 | 2026-03-17 | 1.2.3 Architecture Approval
2.1.1 | Frontend Development | Maaz | 2026-02-04 | 2026-02-25
2.1.2 | Backend Development | Maaz | 2026-02-10 | 2026-03-05 | 2.1.1 Frontend Development
2.1.3 | API Integration | Maaz | 2026-03-06 | 2026-03-17 | 2.1.2 Backend Development
2.2 | Bitrix Configuration | Jasleen | 2026-02-08 | 2026-03-10 | 1.2.3 Architecture Approval
2.2.1 | Setup CRM Modules | Jasleen | 2026-02-08 | 2026-02-25
2.2.2 | Configure Automation Rules | Jasleen | 2026-02-26 | 2026-03-10 | 2.2.1 Setup CRM Modules
2.3 | Dialpad AI Setup | Maaz | 2026-02-18 | 2026-03-10 | 2.1.3 API Integration
2.3.1 | Configure AI Assistant | Maaz | 2026-02-18 | 2026-02-28
2.3.2 | Integrate with Web App | Maaz | 2026-03-01 | 2026-03-10 | 2.3.1 Configure AI Assistant
2.4 | CRM Automation | Jasleen | 2026-02-18 | 2026-03-17 | 2.2.2 Configure Automation Rules
2.4.1 | Workflow Setup | Jasleen | 2026-02-18 | 2026-03-05
2.4.2 | Testing Automation | Jasleen | 2026-03-06 | 2026-03-17 | 2.4.1 Workflow Setup
2.5 | Booking + CRM Sync | Maaz + Jasleen | 2026-03-01 | 2026-03-21 | 2.1.3 API Integration, 2.2.2 Configure Automation Rules
2.5.1 | Data Mapping | Maaz + Jasleen | 2026-03-01 | 2026-03-10
2.5.2 | Sync Testing | Maaz + Jasleen | 2026-03-11 | 2026-03-21 | 2.5.1 Data Mapping
Testing Phase
3.1 | Integration Testing | Deepak | 2026-03-04 | 2026-03-21 | 2.5.2 Sync Testing
3.1.1 | Execute Test Cases | Deepak | 2026-03-04 | 2026-03-15
3.1.2 | Fix Integration Defects | Deepak | 2026-03-16 | 2026-03-21 | 3.1.1 Execute Test Cases
3.2 | UAT Build | Deepak | 2026-03-15 | 2026-03-25 | 3.1.2 Fix Integration Defects
3.2.1 | Prepare UAT Environment | Deepak | 2026-03-15 | 2026-03-20
3.2.2 | Deploy UAT Version | Deepak | 2026-03-21 | 2026-03-25 | 3.2.1 Prepare UAT Environment
3.3 | UAT Approval | Sponsor | 2026-03-22 | 2026-03-29 | 3.2.2 Deploy UAT Version
3.4 | Final Fixes | Deepak | 2026-03-30 | 2026-04-05 | 3.3 UAT Approval
3.4.1 | Apply Final Bug Fixes | Deepak | 2026-03-30 | 2026-04-03
3.4.2 | Regression Testing | Deepak | 2026-04-04 | 2026-04-05 | 3.4.1 Apply Final Bug Fixes
Deployment Phase
4.1 | Production Deployment | Maaz | 2026-04-01 | 2026-04-10 | 3.4.2 Regression Testing
4.1.1 | Production Environment Setup | Maaz | 2026-04-01 | 2026-04-05
4.1.2 | Final Deployment | Maaz | 2026-04-06 | 2026-04-10 | 4.1.1 Production Environment Setup
4.2 | Training & Handoff | Anis | 2026-04-06 | 2026-04-12 | 4.1.2 Final Deployment
4.2.1 | Prepare Training Materials | Anis | 2026-04-06 | 2026-04-09
4.2.2 | Conduct Training Session | Anis | 2026-04-10 | 2026-04-12 | 4.2.1 Prepare Training Materials
4.3 | Final Presentation | Team | 2026-04-14 | 2026-04-19 | 4.2.2 Conduct Training Session